## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a developer, I want JDK 17, MySQL, Maven, and Spring Boot 3.3.1 installed and configured so that the development environment is ready for the team. | MUST HAVE | NONE | Angajala Rahini | 3- Completed
Sprint 1 | Sprint 1 | US-02 | As a developer, I want a Maven project with pom.xml containing all dependencies (Selenium 4.25.0, REST Assured 5.4.0, TestNG 7.10.2, Allure 2.25.0, WebDriverManager 5.8.0, Lombok, MySQL Connector) so that the project builds cleanly. | MUST HAVE | JDK 17, Maven, MySQL | Angajala Rahini | 3- Completed
Sprint 1 | Sprint 1 | US-03 | As a developer, I want a Spring Boot application entry point (RegressionFrameworkApplication.java) and application.properties configured with MySQL datasource, Hibernate DDL auto, and server port 8080 so that the app starts and connects to the database. | MUST HAVE | Maven Project, Spring Boot 3.3.1 | Angajala Rahini | 3- Completed
Sprint 1 | Sprint 1 | US-04 | As a developer, I want a clear package structure (controller / service / repository / model / utils / tests) so that concerns are separated and the codebase is maintainable. | MUST HAVE | Spring Boot Application Setup | Angajala Rahini | 3- Completed
Sprint 2 | Sprint 2 | US-05 | As a developer, I want a TestResult JPA entity with fields id, test_name, status, execution_time, and timestamp mapped to the MySQL 'test_result' table via Spring Data JPA so that every test outcome can be persisted. | MUST HAVE | MySQL, Spring Data JPA, Hibernate | Angajala Rahini | 3- Completed
Sprint 2 | Sprint 2 | US-06 | As a developer, I want a TestResultRepository extending JpaRepository so that CRUD operations on test results are available without boilerplate SQL. | MUST HAVE | TestResult Entity, Spring Data JPA | Angajala Rahini | 3- Completed
Sprint 2 | Sprint 2 | US-07 | As a QA engineer, I want Selenium WebDriver UI test cases (loginTest, getAdminTest) using WebDriverManager for automatic driver management and screenshot capture on failure via a TestNG listener so that browser automation evidence is captured end-to-end. | MUST HAVE | Selenium 4.25.0, WebDriverManager 5.8.0, TestNG | Angajala Rahini | 3- Completed
Sprint 2 | Sprint 2 | US-08 | As a QA engineer, I want REST Assured API test cases (getUserTest, runApiTests, loginTest, getAdminTest) with JSON-driven test data and assertion chains validating response bodies, status codes, and headers so that API correctness is verified automatically. | MUST HAVE | REST Assured 5.4.0, Spring REST API | Angajala Rahini | 3- Completed
Sprint 2 | Sprint 2 | US-09 | As a client, I want Spring Boot REST APIs — POST /tests/integrate and GET /tests/{id} — so that test integration setup and queries can be triggered and monitored programmatically. | MUST HAVE | TestExecutionService, Spring REST Controller | Angajala Rahini | 3- Completed
Sprint 3 | Sprint 3 | US-10 | As a developer, I want a TestExecutionService implementing runTests(), getResults(), getResultsSummary() (pass/fail count + percentage), and getStatus() so that the business logic layer is fully encapsulated. | MUST HAVE | TestResultRepository, Spring Service Layer | Angajala Rahini | 3- Completed
Sprint 3 | Sprint 3 | US-11 | As a QA engineer, I want testng.xml configured for parallel execution (methods/classes) using multiple threads so that UI and API tests run concurrently and suite execution time is reduced. | MUST HAVE | Selenium Tests, REST Assured Tests, TestNG | Angajala Rahini | 3- Completed
Sprint 3 | Sprint 3 | US-12 | As a client, I want Spring Boot APIs — POST /schedule/run and GET /execution/status — so that test suites can be triggered on demand and execution status monitored via HTTP. | MUST HAVE | TestExecutionService, Spring REST Controller | Angajala Rahini | 3- Completed
Sprint 3 | Sprint 3 | US-13 | As a QA manager, I want Allure 2.20.1 reports generated after every test run with drill-down per test case, pass/fail trend chart, suite summary, and failure screenshots so that stakeholders can review results via 'allure serve'. | MUST HAVE | TestNG Listener, MySQL, Allure 2.20.1 | Angajala Rahini | 3- Completed
Sprint 3 | Sprint 3 | US-14 | As a QA engineer, I want a TestNG listener that captures failure screenshots, logs execution metadata, and saves each result to MySQL via the service layer so that every test outcome is fully traceable. | MUST HAVE | Selenium Tests, REST Assured Tests, TestNG Listener | Angajala Rahini | 3- Completed
Sprint 3 | Sprint 3 | US-15 | As a client, I want Spring Boot APIs — GET /reports/generate and POST /logs/collect — so that HTML/CSV reports and failure logs can be accessed and collected programmatically. | SHOULD HAVE | Allure Reports, TestNG Listener, Spring REST Controller | Angajala Rahini | 3- Completed
Sprint 4 | Sprint 4 | US-16 | As a QA manager, I want GET /execution/results/summary to return pass count, fail count, and percentage-based analytics from MySQL so that quality trends are visible across multiple test runs. | MUST HAVE | TestExecutionService, MySQL Analytics | Angajala Rahini | 3- Completed
Sprint 4 | Sprint 4 | US-17 | As a client, I want Spring Boot APIs — GET /analytics/trends and GET /results/{suiteId} — so that regression metrics and suite-level results can be retrieved for visualization. | MUST HAVE | Result Analytics Tracker, MySQL, Spring REST Controller | Angajala Rahini | 3- Completed
Sprint 4 | Sprint 4 | US-18 | As a non-technical user, I want a basic HTML/CSS/JS frontend dashboard (index.html) that triggers POST /execution/run and displays results from GET /execution/results so that the framework can be used without a terminal. | SHOULD HAVE | Spring REST Controller, HTML/CSS/JS | Angajala Rahini | 3- Completed
Sprint 4 | Sprint 4 | US-19 | As a developer, I want a comprehensive README.md documenting project overview, tech stack, architecture layers, execution flow (Trigger→Execute→Parallelize→Persist→Report), API endpoints, and how-to-run steps so that the project is fully reproducible. | MUST HAVE |  | Angajala Rahini | 3- Completed
Sprint 4 | Sprint 4 | US-20 | As a project stakeholder, I want screenshots of UI test execution, API JSON responses, MySQL database table, and Allure report included in the repository and presentation so that project evidence is complete for Infosys SpringBoard evaluation. | MUST HAVE | Allure Reports, Screenshots Folder | Angajala Rahini | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 95 | 14 | 17 | 18 | 12 | 13 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-001 | Install JDK 17, MySQL, Maven and verify all tools are working on local machine | 18/02/2026 | 18/02/2026 | Angajala Rahini | Setup | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-002 | Create Maven project with Spring Boot 3.3.1 parent in pom.xml and set Java 17 | 18/02/2026 | 19/02/2026 | Angajala Rahini | Setup | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-003 | Add all dependencies: Selenium 4.25.0, TestNG 7.10.2, REST Assured 5.4.0 to pom.xml | 19/02/2026 | 19/02/2026 | Angajala Rahini | Configuration | 3- Completed | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-004 | Add Allure 2.25.0, WebDriverManager 5.8.0, Lombok, MySQL Connector to pom.xml | 19/02/2026 | 20/02/2026 | Angajala Rahini | Configuration | 3- Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-005 | Resolve Maven dependency conflicts and verify mvn clean install runs successfully | 20/02/2026 | 20/02/2026 | Angajala Rahini | Configuration | 3- Completed | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-006 | Create RegressionFrameworkApplication.java with @SpringBootApplication main class | 20/02/2026 | 21/02/2026 | Angajala Rahini | Development | 3- Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-007 | Configure application.properties with MySQL datasource, Hibernate DDL auto, port 8080 | 21/02/2026 | 21/02/2026 | Angajala Rahini | Configuration | 3- Completed | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-008 | Start Spring Boot app and verify it connects to MySQL without errors | 21/02/2026 | 24/02/2026 | Angajala Rahini | Testing | 3- Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-009 | Create all package folders: controller, service, repository, model, utils, tests | 24/02/2026 | 24/02/2026 | Angajala Rahini | Setup | 3- Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-05 | T-010 | Create TestResult.java entity with @Entity, @Table, @Id and all 5 fields | 02/03/2026 | 02/03/2026 | T Chandu | Development | 3- Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-011 | Verify Hibernate auto-creates test_result table in MySQL on startup | 02/03/2026 | 03/03/2026 | T Chandu | Testing | 3- Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-012 | Create TestResultRepository.java extending JpaRepository<TestResult, Long> | 03/03/2026 | 03/03/2026 | T Chandu | Development | 3- Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-013 | Implement Selenium UI test cases: loginTest and getAdminTest using WebDriverManager | 03/03/2026 | 06/03/2026 | T Chandu | Testing | 3- Completed | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-014 | Add TestNG listener to capture screenshots on test failure and save to /screenshots folder | 06/03/2026 | 07/03/2026 | T Chandu | Testing | 3- Completed | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-015 | Implement REST Assured API tests: getUserTest, runApiTests with JSON-driven test data | 07/03/2026 | 10/03/2026 | T Chandu | Testing | 3- Completed | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-016 | Add assertion chains for response body, status code, and headers in all API tests | 10/03/2026 | 11/03/2026 | T Chandu | Testing | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-017 | Create TestExecutionController with POST /tests/integrate and GET /tests/{id} endpoints | 11/03/2026 | 12/03/2026 | T Chandu | Development | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-018 | Test POST /tests/integrate and GET /tests/{id} endpoints via Postman | 12/03/2026 | 12/03/2026 | T Chandu | Testing | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-10 | T-019 | Implement TestExecutionService with runTests(), getResults(), getResultsSummary(), getStatus() | 16/03/2026 | 16/03/2026 | T Chandu | Development | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-020 | Configure testng.xml with parallel='methods' and thread-count=3 for concurrent execution | 16/03/2026 | 17/03/2026 | T Chandu | Configuration | 3- Completed | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-021 | Fix NullPointerException in parallel runs by replacing static WebDriver with ThreadLocal | 17/03/2026 | 18/03/2026 | T Chandu | Development | 3- Completed | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-022 | Create ScheduleController with POST /schedule/run and GET /execution/status endpoints | 18/03/2026 | 19/03/2026 | T Chandu | Development | 3- Completed | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-023 | Implement programmatic TestNG runner in service layer to trigger suite via API | 19/03/2026 | 20/03/2026 | T Chandu | Development | 3- Completed | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T-024 | Add Allure 2.20.1 agent argLine in Surefire config in pom.xml and verify report generation | 20/03/2026 | 21/03/2026 | T Chandu | Configuration | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T-025 | Verify Allure report shows 100% pass rate with drill-down, trend chart, and screenshots | 21/03/2026 | 24/03/2026 | T Chandu | Testing | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T-026 | Implement TestNG listener to log metadata and persist each result to MySQL via service | 24/03/2026 | 25/03/2026 | T Chandu | Development | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T-027 | Create ReportController with GET /reports/generate and POST /logs/collect endpoints | 25/03/2026 | 26/03/2026 | T Chandu | Development | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-16 | T-028 | Implement GET /execution/results/summary returning pass count, fail count, and percentage | 27/03/2026 | 27/03/2026 | T Chandu | Development | 3- Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T-029 | Create AnalyticsController with GET /analytics/trends and GET /results/{suiteId} | 27/03/2026 | 28/03/2026 | T Chandu | Development | 3- Completed | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T-030 | Fix GET /results/{suiteId} empty list bug with custom @Query in repository | 28/03/2026 | 28/03/2026 | T Chandu | Development | 3- Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T-031 | Build index.html frontend dashboard with POST /execution/run trigger and results display | 28/03/2026 | 31/03/2026 | T Chandu | Development | 3- Completed | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T-032 | Fix CORS policy error by adding @CrossOrigin on TestExecutionController | 31/03/2026 | 31/03/2026 | T Chandu | Development | 3- Completed | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | T-033 | Write comprehensive README.md with tech stack, architecture, API endpoints, and run steps | 31/03/2026 | 01/04/2026 | T Chandu | Documentation | 3- Completed | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-20 | T-034 | Add screenshots of UI tests, API responses, MySQL table, and Allure report to repository | 01/04/2026 | 02/04/2026 | T Chandu | Documentation | 3- Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 – 18 Feb | None | Environment setup started; JDK 17, MySQL, and Maven installed successfully on all machines.
Sprint 1 | Day 2 – 19 Feb | Dependency conflict: Allure 2.25.0 and TestNG 7.10.2 scoping issue caused build failure | Moved Allure to compile scope; pinned TestNG to test scope; mvn clean install passed successfully.
Sprint 1 | Day 3 – 20 Feb | MySQL connection refused — wrong port configured in application.properties | Corrected datasource URL to jdbc:mysql://localhost:3306/testdb; Spring Boot connected to MySQL successfully.
Sprint 1 | Day 5 – 24 Feb | None | Spring Boot app running on port 8080; Hibernate auto-created test_result table; Sprint 1 tasks complete.
Sprint 2 | Day 1 – 02 Mar | None | TestResult entity created; @Table(name='test_result') confirmed; schema verified in MySQL Workbench.
Sprint 2 | Day 3 – 06 Mar | WebDriverManager could not download ChromeDriver on restricted network | Used local ChromeDriver binary path as fallback; added system property override in Selenium test setup.
Sprint 2 | Day 5 – 10 Mar | REST Assured test getUserTest throwing JsonPathException on response parsing | Switched to .extract().response().asString() and used JSONPath manually; test passing correctly.
Sprint 2 | Day 7 – 12 Mar | POST /tests/integrate returning HTTP 500 on first invocation | Debugged null pointer in service layer; added @Autowired on repository bean; endpoint returning 200 OK.
Sprint 2 | Day 9 – 14 Mar | None | All Sprint 2 tasks complete; Selenium and REST Assured tests passing; REST APIs verified via Postman.
Sprint 3 | Day 1 – 16 Mar | None | Parallel execution setup started; testng.xml configured with parallel='methods' and thread-count=3.
Sprint 3 | Day 3 – 18 Mar | Parallel execution causing NullPointerException — shared static WebDriver instance | Replaced static WebDriver with ThreadLocal<WebDriver>; each thread gets isolated driver instance; issue resolved.
Sprint 3 | Day 5 – 20 Mar | Allure results directory not found after mvn test — report not generating | Added Allure agent argLine in Surefire config in pom.xml; allure-results directory created; report generated.
Sprint 3 | Day 7 – 24 Mar | POST /schedule/run not triggering TestNG runner programmatically | Added TestNG programmatic runner in service layer using TestNG API; endpoint triggering test suite correctly.
Sprint 3 | Day 9 – 26 Mar | None | Sprint 3 complete; parallel execution stable; Allure report showing 100% pass rate; all scheduling APIs working.
Sprint 4 | Day 1 – 27 Mar | None | Analytics tracker development started; GET /analytics/trends endpoint skeleton created.
Sprint 4 | Day 3 – 31 Mar | GET /results/{suiteId} returning empty list for valid suite IDs | Fixed query method in repository; added custom @Query to filter by suite ID; endpoint returning correct data.
Sprint 4 | Day 4 – 01 Apr | HTML dashboard POST /execution/run call blocked by CORS policy in browser | Added @CrossOrigin annotation on TestExecutionController; dashboard trigger working correctly.
Sprint 4 | Day 5 – 02 Apr | None | All 4 modules complete; end-to-end tests passing; README updated; screenshots added to repository.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 18/02/2026 | 28/02/2026 | Angajala Rahini | Verify mvn clean install after every new pom.xml dependency addition | Adding multiple dependencies at once without intermediate build verification | Testing Spring Boot startup after every major configuration change | Incremental build checks adopted; no surprise failures mid-sprint
2 | Sprint 1 | 18/02/2026 | 28/02/2026 | T.Chandu | Document environment setup steps in README immediately after configuration | Assuming setup is obvious and skipping documentation for later | Cross-checking application.properties settings before running the app | README updated with full MySQL setup, datasource config, and run instructions
3 | Sprint 2 | 02/03/2026 | 14/03/2026 | Sahithi | Use WebDriverWait (explicit waits) for all Selenium element interactions from the start | Using Thread.sleep() or implicit waits as shortcuts for dynamic elements | Using WebDriverManager to auto-manage browser driver binaries | All Selenium tests refactored to use explicit waits; flakiness eliminated
4 | Sprint 2 | 02/03/2026 | 14/03/2026 | Pavithra | Validate REST Assured response body fields using JSONPath assertions, not just status codes | Marking tests as passed just because HTTP status code returned 200 | Keeping REST Assured request/response specs in a shared reusable base class | Full JSON body assertions added to getUserTest and runApiTests test cases
5 | Sprint 3 | 16/03/2026 | 26/03/2026 | Srinu | Use ThreadLocal<WebDriver> pattern from the very start whenever parallel execution is needed | Using a single static WebDriver instance across test classes in parallel runs | Reviewing Allure report after every test run to detect new failures early | ThreadLocal driver setup applied across all UI tests; parallel execution now stable
6 | Sprint 3 | 16/03/2026 | 26/03/2026 | Lavkush Nishad | Configure Allure agent in pom.xml Surefire argLine at the start of the sprint before writing tests | Deferring Allure and reporting setup until after all tests are written | Using Postman collections to systematically test every new REST endpoint added | Allure pom.xml config done at sprint start; reports auto-generated after every mvn test run
7 | Sprint 4 | 2026-03-27 | 02/04/2026 | All Team Members | Run full end-to-end integration tests across all 4 modules before sprint closure | Testing individual modules in isolation without verifying cross-module integration | Collaborating on final validation by reviewing each other's API outputs and test results | Full end-to-end flow (Trigger→Execute→Persist→Report→Analytics) validated and confirmed working by all members
8 | Sprint 4 | 2026-03-31 | 2026-04-02 | Angajala Rahini | Add @CrossOrigin on controllers from day one when frontend integration is planned | Testing REST endpoints only in Postman without verifying browser/frontend integration | Building lightweight HTML dashboards to make APIs accessible to non-technical users | CORS fixed; HTML dashboard successfully triggering POST /execution/run and displaying results